International School

Capstone Project 1

CMU-SE 450 – C1SE.30

Product Backlog

Version 1.1

Date: September 16th, 2026

TEST COVERAGE ANALYSIS AND AI-DRIVEN TEST GENERATION SYSTEM

Submitted by

Dinh, Huynh Tan

Phuc, Tran Huu

Quy, Nguyen Duy

Thuan, Ngo Huu

Approved by

Man, Nguyen Duc, Ph.D.

Proposal Review Panel Representative:

Name				Signature		Date

Capstone Project 1- Mentor:

Name				Signature		Date

PROJECT INFORMATION

| Project acronym | COVAI |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Title | Test Coverage Analysis and AI-Driven Test Generation System |  |  |  |  |
| Start Date | Aug 10, 2026 | End Date | Dec 12, 2026 |  |  |
| Lead Institution | International School, Duy Tan University |  |  |  |  |
| Project Mentor | Man, Nguyen Duc, Ph.D. |  |  |  |  |
| Scrum master / Project Leader & contact details | Dinh, Huynh Tan Email: huynhtandinh.dev@gmail.com Tel: 0365 472 162 ID: 29219052500 |  |  |  |  |
| Partner Organization | Duy Tan University |  |  |  |  |
| Project Web URL |  |  |  |  |  |
| Team members | Name | Email |  |  | Tel |
| 29219052500 | Dinh, Huynh Tan | huynhtandinh.dev@gmail.com |  | 0365472162 |  |
| 29211458179 | Phuc, Tran Huu | phuc12435az@gmail.com |  | 0842644169 |  |
| 29211158823 | Quy, Nguyen Duy | quylavip333@gmail.com |  | 0334814522 |  |
| 29219065178 | Thuan, Huu Ngo | thuanhuugl@gmail.com |  | 0385591447 |  |

DOCUMENT APPROVALS

The following signatures are required for approval of this document.

| Dinh, Huynh Tan Student ID: 29219052500 Scrum Master | Signature | Date |
| --- | --- | --- |
| Phuc, Tran Huu Student ID: 29211458179 Team Member | Signature | Date |
| Quy, Nguyen Duy Student ID: 29211158823 Team Member | Signature | Date |
| Thuan, Ngo Huu Student ID: 29219065178 Team Member | Signature | Date |

PRODUCT BACKLOG DOCUMENT

| Document Title | Product Backlog Document |  |  |
| --- | --- | --- | --- |
| Author(s) | Thuan, Ngo Huu |  |  |
| Role | Frontend Lead / Full-Stack Developer |  |  |
| Date | September 16, 2026 | File name: | C1SE.30_ProductBacklog_CovAI_ver1.1.docx |

REVISION HISTORY

| Version | Date | Comments | Author |
| --- | --- | --- | --- |
| 1.0 | Sep 16, 2026 | Initial Product Backlog Document | Dinh |
| 1.1 | Sep 16, 2026 | Update Document | Thuan |

TABLE OF CONTENTS

1. Introduction	1

1.1 Purpose	1

1.2 Scope	1

1.3 System Overview	2

2. Product Backlog	3

2.1 Priority and Estimates	3

2.2 Product Backlog Specification (Admin)	8

2.3 Product Backlog Specification (User)	9

3. Constraints	17

4. Stakeholders and User Descriptions Summary	18

5. References	19

LIST OF TABLES

Table 1 - Priority Definition	3

Table 2 - Development Effort and Sprint Allocation	4

Table 3 - Sprint 1 Work Breakdown (Week 1 & Week 2)	5

Table 4 - Product Backlog Specification (Admin)	8

Table 5 - Product Backlog Specification (User)	9

Table 6 - Constraints	17

Table 7 - Stakeholders and User Descriptions Summary	18

Table 8 - References	19

1. Introduction

The agile product backlog in Scrum is a prioritized features list, containing short descriptions of all functionality desired in the product. When applying Scrum, it’s not necessary to start a project with a lengthy, upfront effort to document all requirements. Typically, a Scrum team and its product owner begin by writing down everything they can think of for agile backlog prioritization. This agile product backlog is almost always more than enough for a first sprint. The Scrum product backlog is then allowed to grow and change as more is learned about the product and its clients.

  - Purpose

- Provide a prioritized features list, containing short descriptions of all functionality desired in the CovAI product.

- Lists everything that the product owner and Scrum team feel should be included in the software they are developing for automated test coverage analysis, AI-driven test generation, and AI chatbot trustworthiness evaluation.

1.2 Scope

- The Product Backlog defines exactly two operational modules: Admin and User. Developers, QA engineers, testers, AI engineers, domain experts, and project owners use the same User module to test and evaluate their projects; no additional product module is created for these project personas.

- Specifies all functional requirements (FR-01 to FR-16) and non-functional quality attributes (NFR-01 to NFR-08) across the CovAI platform.

- Lists key capabilities across two core pillars: (1) Software Testing & Coverage Intelligence: ZIP/GitHub ingestion, isolated Docker sandbox execution, Statement/Branch/Function/Line coverage, AST & interactive CFG visualization, Cyclomatic Complexity analysis, Google Gemini AI test skeleton and full test generation, multi-framework support (Jest, Vitest, Supertest, Cypress, Playwright), GitHub webhooks, and real-time WebSocket notifications; (2) AI Chatbot Trustworthiness Evaluation: Knowledge document ingestion, evaluation profile builder, scenario generation, multi-task evaluation runner (Knowledge Q&A, Usage Guidance, Action/Tool execution), tool/action safety verification, 3-layer trustworthiness scoring (Core Criteria, Task Module, Project Rules), diagnosis, and multi-version benchmark comparison.

- Provides concise descriptions of desired functionality and user value for each backlog item.

- Assigns three standard priority levels (High, Medium, Low) and development effort (hours) aligned with the 7 Sprints of the project schedule.

1.3 System Overview

CovAI is designed with a decoupled architecture comprising React 19 + Vite frontend, Express.js 5 REST API, PostgreSQL + Prisma ORM database, BullMQ + Redis job queues, Docker sandbox test execution, and Google Gemini API integration.

2. Product Backlog

2.1 Priority and Estimates

In accordance with Agile/Scrum empirical process control and CMU-SE 450 capstone guidelines, the Product Backlog features are evaluated and prioritized into three standard categories: High, Medium, and Low. Every feature is sized in committed man-hours and assigned to specific iterations across the 7 Sprints of the CovAI development lifecycle.

Table 1 - Priority Definition

| Priority Level | Definition | Scope & Criteria | Target Sprints |
| --- | --- | --- | --- |
| High | Critical functionality required for the MVP and defense-ready core workflow. | Authentication, project management, source ingestion, Docker test execution, coverage, AI test generation, chatbot evaluation, dashboard, end-to-end testing, and deployment. | Sprint 1–7 |
| Medium | Important analytical, automation, security, and operational capabilities that strengthen the MVP. | CFG/complexity analysis, multi-framework adapters, queue monitoring, GitHub webhook automation, ground-truth management, diagnosis/comparison, and security verification. | Sprint 3–7 |
| Low | Useful non-blocking enhancements that can be deferred without preventing the core workflow. | Real-time WebSocket notifications and other supplementary presentation or convenience improvements. | Sprint 4 |

The CovAI engineering effort encompasses 7 Agile/Scrum Sprints comprising 1,920 development hours. The companion XLSX records the detailed acceptance criteria, remarks, status, type, project ID, sprint number, and numeric estimate for each of the 33 canonical user stories. Sprint 1 is reconciled directly to the Project Plan: 36 tasks, 336 hours total, with Week 1 = 168 hours and Week 2 = 168 hours.

Table 2 - Development Effort and Sprint Allocation

| Sprint | Major Focus & Key Deliverables | Duration | Schedule Dates | Committed Hours |
| --- | --- | --- | --- | --- |
| Sprint 1 | Environment Setup, Authentication & Project Management | 14 days | Sep 14, 2026 – Sep 27, 2026 | 336 hours |
| Sprint 2 | Source Ingestion, Test Execution & Coverage Analysis | 14 days | Sep 28, 2026 – Oct 11, 2026 | 336 hours |
| Sprint 3 | Code Analysis, Multi-Test Framework Support & AI Test Generation | 14 days | Oct 12, 2026 – Oct 25, 2026 | 336 hours |
| Sprint 4 | GitHub Automation, Monitoring & System Integration | 6 days | Oct 26, 2026 – Oct 31, 2026 | 144 hours |
| Sprint 5 | AI Chatbot Trustworthiness Evaluation Module | 14 days | Nov 08, 2026 – Nov 21, 2026 | 336 hours |
| Sprint 6 | End-to-End System Testing & Quality Assurance | 7 days | Nov 22, 2026 – Nov 28, 2026 | 168 hours |
| Sprint 7 | System Deployment, Final Fixes & Project Delivery | 11 days | Nov 29, 2026 – Dec 09, 2026 | 264 hours |
| Total Development | Total Development Effort across 7 Sprints (4 members @ 6h/day) | 80 days | Sep 14, 2026 – Dec 09, 2026 | 1,920 hours |
| Total Project | Total Committed Academic Man-Hours (including Initial Phase & Defense) | 107 days | Aug 10, 2026 – Dec 26, 2026 | 2,568 hours |

Sprint 1 is structured into two 1-week cycles totaling 336 man-hours (24 man-hours/day across 4 team members). Week 1 (14/09/2026 - 20/09/2026) delivers 168 man-hours focused on UI prototyping, database schema engineering, front-end views, and foundational back-end controllers. Week 2 (21/09/2026 - 27/09/2026) delivers 168 man-hours completing back-end API services, authentication middleware, Docker host setup, and comprehensive unit test suites. Table 7 outlines the complete task breakdown matching the verified Project Plan.

Table 3 - Sprint 1 Work Breakdown (Week 1 & Week 2)

| Week | Component | No | Task Name | Responsible Member | Estimate |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Design UI | 1 | UI Home Page | Thuan, Ngo Huu | 8 hours |
| Week 1 | Design UI | 2 | UI Registration | Phuc, Tran Huu | 8 hours |
| Week 1 | Design UI | 3 | UI Login | Dinh, Huynh Tan | 8 hours |
| Week 1 | Design UI | 4 | UI Landscape | Dinh, Huynh Tan | 8 hours |
| Week 1 | Design UI | 5 | UI Forgot Password | Quy, Nguyen Duy | 8 hours |
| Week 1 | Design UI | 6 | UI Profile User | Phuc, Tran Huu | 8 hours |
| Week 1 | Design UI | 7 | UI GitHub Repository | Thuan, Ngo Huu | 8 hours |
| Week 1 | Design UI | 8 | UI Project Management | Thuan, Ngo Huu | 8 hours |
| Week 1 | Design UI | 9 | UI Snapshot Management | Phuc, Tran Huu | 8 hours |
| Week 1 | Database | 10 | Design database (PostgreSQL & Prisma ORM) | Quy, Nguyen Duy / Thuan, Ngo Huu | 24 hours |
| Week 1 | Front end | 11 | (Front-end) Homepage | Quy, Nguyen Duy | 8 hours |
| Week 1 | Front end | 12 | (Front-end) Landscape | Quy, Nguyen Duy | 8 hours |
| Week 1 | Front end | 13 | (Front-end) Registration | Thuan, Ngo Huu | 8 hours |
| Week 1 | Front end | 14 | (Front-end) Login | Phuc, Tran Huu | 8 hours |
| Week 1 | Front end | 15 | (Front-end) Forgot Password | Dinh, Huynh Tan | 8 hours |
| Week 1 | Front end | 16 | (Front-end) GitHub Repository | Phuc, Tran Huu | 8 hours |
| Week 1 | Front end | 17 | (Front-end) Project Management | Quy, Nguyen Duy | 8 hours |
| Week 1 | Back end | 18 | (Back-end) Forgot Password | Dinh, Huynh Tan | 16 hours |
| Week 1 Subtotal | Week 1 Total Effort (14/09/2026 - 20/09/2026: 7 days @ 24h/day) | - | - | All 4 Members | 168 hours |
| Week 2 | Back end | 19 | (Back-end) Reset Password | Dinh, Huynh Tan | 16 hours |
| Week 2 | Back end | 20 | (Back-end) Registration | Phuc, Tran Huu | 16 hours |
| Week 2 | Back end | 21 | (Back-end) Login & Session | Thuan, Ngo Huu | 16 hours |
| Week 2 | Back end | 22 | (Back-end) User Profile & PAT | Quy, Nguyen Duy | 16 hours |
| Week 2 | Back end | 23 | (Back-end) GitHub Repository | Dinh, Huynh Tan | 16 hours |
| Week 2 | Back end | 24 | (Back-end) Environment Setup & Docker Host | Phuc, Tran Huu | 16 hours |
| Week 2 | Back end | 25 | (Back-end) Authentication Middleware | Thuan, Ngo Huu | 16 hours |
| Week 2 | Back end | 26 | (Back-end) Snapshot Management | Quy, Nguyen Duy | 16 hours |
| Week 2 | Testing | 27 | Design Test Case for Registration | Dinh, Huynh Tan | 4 hours |
| Week 2 | Testing | 28 | Design Test Case for Login | Phuc, Tran Huu | 4 hours |
| Week 2 | Testing | 29 | Design Test Case for Forgot Password | Thuan, Ngo Huu | 4 hours |
| Week 2 | Testing | 30 | Design Test Case for Reset Password | Phuc, Tran Huu | 4 hours |
| Week 2 | Testing | 31 | Design Test Case for Profile | Dinh, Huynh Tan | 4 hours |
| Week 2 | Testing | 32 | Design Test Case for Homepage | Thuan, Ngo Huu | 4 hours |
| Week 2 | Testing | 33 | Design Test Case for Landscape | Quy, Nguyen Duy | 4 hours |
| Week 2 | Testing | 34 | Design Test Case for GitHub Repository | Dinh, Huynh Tan | 4 hours |
| Week 2 | Testing | 35 | Design Test Case for Project Management | Quy, Nguyen Duy | 4 hours |
| Week 2 | Testing | 36 | Design Test Case for Snapshot Management | Phuc, Tran Huu | 4 hours |
| Week 2 Subtotal | Week 2 Total Effort (21/09/2026 - 27/09/2026: 7 days @ 24h/day) | - | - | All 4 Members | 168 hours |
| Sprint 1 Total | Complete Sprint 1 Committed Work (36 tasks across 14 calendar days) | - | - | All 4 Members | 336 hours |

2.2 Product Backlog Specification (Admin)

Table 4 - Product Backlog Specification (Admin)

| ID | Theme | As a/an | I want to | So that | Priority |
| --- | --- | --- | --- | --- | --- |
| PB-20 | Asynchronous BullMQ Queue & Worker Monitoring [Sprint 4 ¦ 40h] | Admin | Manage and monitor BullMQ background job queues and worker execution states in real-time | I can ensure smooth asynchronous analysis, detect queue bottlenecks, and retry failed tasks | Medium |
| PB-31 | Security Hardening, Quotas & Container Sandboxing Verification [Sprint 6 ¦ 72h] | Admin | Conduct security penetration checks, rate-limit verifications, and Docker sandbox escape audits | The platform is robustly defended against malicious code execution, token depletion, and unauthorized data access | Medium |
| PB-32 | Production Deployment & Docker Compose Multi-Container Orchestration [Sprint 7 ¦ 144h] | Admin | Deploy the complete CovAI platform using Docker Compose multi-container orchestration | The client, server, Redis, and PostgreSQL services run reliably in production for defense demo and user trials | High |
| PB-33 | Admin Platform Oversight, Audit Logs & API Quota Management [Sprint 7 ¦ 120h] | Admin | Monitor system-wide platform health, view audit logs, and configure global Gemini AI token limits | I can ensure operational stability, track user usage patterns, and prevent unexpected infrastructure expenses | Medium |

2.3 Product Backlog Specification (User)

Table 5 - Product Backlog Specification (User)

| ID | Theme | As a/an | I want to | So that | Priority |
| --- | --- | --- | --- | --- | --- |
| PB-01 | User Registration & Account Management [Sprint 1 ¦ 36h] | User | Register an account with email, name, and strong password, and verify credentials | I can create an authenticated user profile to securely access the CovAI platform | High |
| PB-02 | User Login & JWT Session Management [Sprint 1 ¦ 52h] | User | Log in with email and password, receive a signed JWT token, and authenticate API requests | I can securely access protected endpoints and maintain an active session | High |
| PB-03 | Password Recovery & Secure Reset Workflow [Sprint 1 ¦ 56h] | User | Request a password reset link via email and reset password using a secure one-time token | I can regain access to my account if I forget my credentials | High |
| PB-04 | User Profile & Encrypted GitHub Token Configuration [Sprint 1 ¦ 28h] | User | View/update my profile details and configure my GitHub Personal Access Token (PAT) | CovAI can authenticate against GitHub APIs to clone private repositories securely | High |
| PB-05 | Platform Navigation & Project Management Workspace [Sprint 1 ¦ 60h] | User | Navigate Homepage and Landscape overview, and manage projects (create, view, edit, delete) | I can organize repositories, view status overviews, and maintain project configurations | High |
| PB-06 | GitHub Repository Ingestion Setup [Sprint 1 ¦ 36h] | User | Link GitHub repositories to projects by specifying repository URL and branch | The system can pull remote source code for automated testing and coverage analysis | High |
| PB-07 | Snapshot Management & Core Database Infrastructure [Sprint 1 ¦ 68h] | User | Create immutable snapshots for source versions and query version histories | I can track code quality over time, compare test runs, and ensure reproducibility | High |
| PB-08 | Local ZIP Archive Project Ingestion [Sprint 2 ¦ 64h] | User | Upload project source code as a ZIP archive with automated sanitization and safety checks | I can analyze local codebases while protecting the server against malicious archives | High |
| PB-09 | GitHub Repository Shallow Clone Ingestion [Sprint 2 ¦ 64h] | User | Import remote repositories directly from GitHub via automated shallow cloning | I can analyze hosted repositories without manual packaging or file transfers | High |
| PB-10 | Automated Testing Framework Detection [Sprint 2 ¦ 64h] | User | Have the system automatically inspect project structure and detect configured testing frameworks | I don't have to manually configure test runners, config paths, and coverage reporters | High |
| PB-11 | Isolated Docker Sandbox Test Execution [Sprint 2 ¦ 80h] | User | Execute automated test suites inside an isolated, resource-constrained Docker container | Tests execute securely without risking host compromise, dependency pollution, or resource exhaustion | High |
| PB-12 | Multi-Level Code Coverage Analysis [Sprint 2 ¦ 64h] | User | View comprehensive test coverage metrics across Statement, Branch, Function, and Line dimensions | I can precisely identify which source files and logic paths are tested versus uncovered | High |
| PB-13 | AST Parsing & Interactive Control Flow Graph (CFG) [Sprint 3 ¦ 64h] | User | Parse JavaScript/TypeScript ASTs and inspect interactive Control Flow Graphs for functions | I can visually trace execution branching and distinguish covered from uncovered execution paths | Medium |
| PB-14 | Cyclomatic Complexity & Testing Gap Prioritization [Sprint 3 ¦ 56h] | User | Calculate Cyclomatic Complexity for every function and get a prioritized list of testing gaps | I can focus testing effort on high-risk, defect-prone functions with low coverage and high complexity | Medium |
| PB-15 | Multi-Framework Test Runner Adapters [Sprint 3 ¦ 48h] | User | Execute tests across Unit, Integration, and E2E frameworks (Jest, Vitest, Supertest, Playwright, Cypress) | I can evaluate test coverage and execution health across all layers of the testing pyramid | Medium |
| PB-16 | AI-Assisted Test Skeleton Generation via Gemini API [Sprint 3 ¦ 56h] | User | Request AI-generated test skeletons for uncovered functions using Google Gemini API | I can quickly get scaffolded test structures, describe blocks, and mock setups for untested code | High |
| PB-17 | AI-Assisted Full Runnable Test Case Generation [Sprint 3 ¦ 64h] | User | Generate complete, runnable unit test implementations targeting specific uncovered branches | I can directly run generated tests to close coverage gaps without writing boilerplate setup manually | High |
| PB-18 | Generated Test Case Validation & Code Export [Sprint 3 ¦ 48h] | User | Review, edit, validate in sandbox, and export AI-generated test files into my project | I can verify test correctness and safely integrate new test suites into my codebase | Medium |
| PB-19 | GitHub Webhook Automation & Continuous Analysis [Sprint 4 ¦ 40h] | User | Configure GitHub repository webhooks to automatically trigger test runs upon new commits or PRs | My project coverage and quality scores are continuously analyzed without manual trigger actions | Medium |
| PB-21 | Real-Time WebSocket Push Notifications [Sprint 4 ¦ 32h] | User | Receive real-time WebSocket push notifications when long-running analysis or AI generation completes | I don't have to repeatedly refresh the browser or wait idle on the screen during background processing | Low |
| PB-22 | Software Quality Overview Dashboard & Radar Metrics [Sprint 4 ¦ 32h] | User | View a centralized Quality Dashboard with composite quality scores and multi-dimensional radar charts | I can holistically evaluate software release readiness across coverage, complexity, and maintainability | High |
| PB-23 | AI Evaluation Knowledge Ingestion & Document Parsing [Sprint 5 ¦ 48h] | User | Upload project business documents, API specifications, FAQ files, and operational rule sets | CovAI can establish the project ground truth required for evaluating internal chatbot trustworthiness | Medium |
| PB-24 | Evaluation Profile Builder & Benchmark Scenario Generation [Sprint 5 ¦ 56h] | User | Configure target chatbot endpoints and automatically generate candidate evaluation scenarios | I can create a structured benchmark dataset covering Knowledge Q&A, Usage Guidance, and Action/Tool execution | High |
| PB-25 | Domain Expert Rule & Ground Truth Confirmation [Sprint 5 ¦ 40h] | User | Review, edit, approve, or add ground truth facts, expected UI sequences, and forbidden actions | The evaluation benchmark precisely reflects validated business logic and prevents false positive penalties | Medium |
| PB-26 | Multi-Task Chatbot Evaluation Runner [Sprint 5 ¦ 56h] | User | Execute automated benchmark evaluation runs against the target chatbot interface | The system systematically tests all approved scenarios and captures raw responses, latency, and metadata | High |
| PB-27 | Chatbot Tool & Action Execution Safety Verification [Sprint 5 ¦ 48h] | User | Verify tool selection accuracy, parameter schemas, safety confirmations, and forbidden actions | I can prevent risky external mutations and ensure the chatbot safely adheres to API authorization rules | High |
| PB-28 | 3-Layer Trustworthiness Multi-Dimensional Scoring Engine [Sprint 5 ¦ 48h] | User | Evaluate chatbot outputs across the 3-Layer framework (Core Criteria, Task Module, Project Rules) | I receive objective, multi-dimensional scores on Correctness, Faithfulness, Hallucination, Safety, and Latency | High |
| PB-29 | Chatbot Diagnosis, Benchmark Comparison & Report Export [Sprint 5 ¦ 40h] | User | Inspect detailed failure diagnosis, compare multiple chatbot versions/models, and export benchmark reports | I can identify root causes of chatbot errors, track model improvements, and present compliance evidence | Medium |
| PB-30 | End-to-End System Integration & Regression Testing [Sprint 6 ¦ 96h] | User | Perform automated end-to-end integration and regression test runs across the complete platform pipeline | I can ensure all interconnected modules (Ingestion -> Sandbox -> Coverage -> CFG -> AI -> Evaluation) work seamlessly | High |

3. Constraints

Table 6 - Constraints

| Constraint | Condition |
| --- | --- |
| Time | Project development duration is 18, structured into 7 Agile/Scrum Sprints |
| People constraint | The project is designed, engineered, and maintained by a dedicated team of 4 software engineering students from Duy Tan University under the academic supervision of Ph.D. Nguyen Duc Man. Total committed development effort is 2,568 man-hours (642 hours per member, based on 6 working hours/day). |
| Hardware & OS | Development is conducted on personal Windows 10/11 and Linux workstations. Server runtime requires Docker Engine 24+ and Node.js 20 LTS. Test sandboxes execute within <=1 GB RAM, <=1 vCPU, and a 30-second timeout. |
| Software & Runtime | Client built with React 19 and Vite; API built with Express.js 5 and Node.js 20 LTS; Database is PostgreSQL managed via Prisma ORM; Job queues are powered by BullMQ and Redis; AI capabilities integrate Google Gemini API. |
| Economic & AI Budget | Direct project budget is 800,000–1,150,000 VND (approximately 50 USD); student labor is non-billable academic effort. Content hashing (SHA-256) and snapshot caching control repeated analysis and AI token expenses. |
| Standards & Quality | Development strictly adheres to Product Owner requirements, Agile/Scrum empirical process control, ISO/IEC/IEEE 29119 Software Testing standards, ISO/IEC 25010 Software Quality models, and IEEE 830/29148 requirements specifications. |
| Safety & Real-World Protection | Evaluation of action-oriented chatbots and dynamic test execution strictly avoids unintended real-world side effects through simulated tool environments, mandatory human confirmation rules for destructive actions, and strict rate limiting. |

4. Stakeholders and User Descriptions Summary

Table 7 - Stakeholders and User Descriptions Summary

| Name | Description | Role |
| --- | --- | --- |
| Product Owner | Provides product vision, defines acceptance criteria, reviews Sprint deliverables, and accepts system increments. | Duy Tan University / Man, Nguyen Duc, Ph.D. |
| Scrum Master / Project Leader | Leads agile processes, facilitates Daily Scrums and Sprint Planning, removes technical impediments, and ensures timely milestone delivery. | Dinh, Huynh Tan |
| Frontend Lead / Full-Stack Developer | Architects React 19 SPA, designs responsive UI/UX, interactive CFG graphs, real-time coverage dashboards, and notification components. | Thuan, Ngo Huu |
| Backend & Integration Developer | Builds RESTful APIs, database schema, BullMQ worker queues, Docker Sandbox isolation environments, and end-to-end integration. | Phuc, Tran Huu |
| Data & Full-Stack Developer | Develops data analysis pipelines, Babel AST parser, CFG generator, database query optimization, and UI modules. | Quy, Nguyen Duy |
| AI Evaluator / Domain Expert | Defines chatbot evaluation profiles, validates ground truth rules and expected actions, audits benchmark scenarios, and analyzes trustworthiness scores. | AI Evaluation Specialist / Domain Expert |
| System Administrator | Manages cloud infrastructure, Docker host environments, BullMQ queues, database backups, security audits, and Gemini API quotas. | C1SE.30 Team |
| Software Developer (End-User) | Primary user who imports projects, executes automated test suites, inspects coverage/CFG graphs, and generates test cases via AI. | Software Developers & Students |
| QA Engineer / Tester (End-User) | Evaluates test coverage metrics, traces requirements to tests, prioritizes coverage gaps, audits AI-generated tests, and exports quality reports. | QA Engineers & Testers |

5. References

Table 8 - References

| No | Reference | Note |
| --- | --- | --- |
| 1 | https://www.scrum.org/resources/scrum-guide | Scrum Guide & Agile Product Backlog Standards |
| 2 | https://www.mountaingoatsoftware.com/agile/scrum/product-backlog/example/ | Scrum Product Backlog Example & Estimation |
| 3 | C1SE.30_Proposal_ver1.2.pdf | CovAI Project Proposal Document (version 1.2) |
| 4 | C1SE.30_ProjectPlan_ver_1.1-C1SE.30_Sprint1_COVAI_ver_1.0.pdf | CovAI Project Plan & Sprint Schedule Document (version 1.1) |
| 5 | https://ai.google.dev/gemini-api/docs | Google Gemini API Documentation |
| 6 | https://www.iso.org/standard/81291.html | ISO/IEC/IEEE 29119 Software Testing Standards |
| 7 | https://www.iso.org/standard/35733.html | ISO/IEC 25010 Systems and Software Quality Requirements and Evaluation |
| 8 | https://is.duytan.edu.vn/en/programs-curriculum/software-engineering/1/20/course-description-bachelor-degree-in-software-engineering/613 | Official CMU-SE 450 course description and staged capstone deliverables |