## Sprint 1
SPRINT 1 |  |  |  |  | BURN DOWN CHART SPRINT 1
Project Name: |  | COVAI
Module Name: |  | Sprint 1
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 2
SPRINT 2 |  |  |  |  | BURN DOWN CHART SPRINT 2
Project Name: |  | COVAI
Module Name: |  | Sprint 2
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 3
SPRINT 3 |  |  |  |  | BURN DOWN CHART SPRINT 3
Project Name: |  | COVAI
Module Name: |  | Sprint 3
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 4
SPRINT 4 |  |  |  |  | BURN DOWN CHART SPRINT 4
Project Name: |  | COVAI
Module Name: |  | Sprint 4
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 5
SPRINT 5 |  |  |  |  | BURN DOWN CHART SPRINT 5
Project Name: |  | COVAI
Module Name: |  | Sprint 5
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 6
SPRINT 6 |  |  |  |  | BURN DOWN CHART SPRINT 6
Project Name: |  | COVAI
Module Name: |  | Sprint 6
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished

## Sprint 7
SPRINT 7 |  |  |  |  | BURN DOWN CHART SPRINT 7
Project Name: |  | COVAI
Module Name: |  | Sprint 7
Development Team: |  | C1SE.30
Start Date: |  | 2026-09-14
End Date: |  | 2026-09-27
No. | Member Name |  | Estimate (hours)
1 | Dinh, Huynh Tan | Dinh | 28
2 | Quy, Ngyen Duy | Quy | 28
3 | Thuan, Huu Ngo | Thuan | 28
4 | Phuc, Tran Huu | Phuc | 28
Total |  |  | 112
ESTIMATE
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 2 | UI Registration | Phuc | 2 | 2026-09-14: 2; 2026-09-15: 0
| 5 | UI Forgot Password | Quy | 4 | 2026-09-14: 2; 2026-09-15: 2; 2026-09-16: 0
| 4 | UI Landscape | Dinh | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 6 | UI Profile User | Phuc | 2 | 2026-09-14: -; 2026-09-15: 2; 2026-09-16: 0
| 3 | UI Login | Dinh | 4 | 2026-09-14: 2; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 9 | UI Snapshot | Phuc | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 0
| 7 | UI GitHub Repository | Thuan | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 8 | UI Project | Thuan | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
Database | 10 | Design database | Quy, Thuan | 8 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: 4; 2026-09-19: 4; 2026-09-20: 0
Front end | 11 | (Front-end) Homepage | Quy | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: 2; 2026-09-17: 2; 2026-09-18: 0
| 14 | (Front-end) Login | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 15 | (Front-end) Forgot Password | Dinh | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 0
| 12 | (Front-end) Landscape | Quy | 2 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -; 2026-09-20: 2; 2026-09-21: 0
| 16 | (Front-end) GitHub Repository | Phuc | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: 2; 2026-09-20: 2; 2026-09-21: 0
| 13 | (Front-end) Registration | Thuan | 2 | - | - | - | - | - | - | - | 2 | 0
| 17 | (Front-end) Project Management | Quy | 2 | - | - | - | - | - | - | - | 2 | 0
Back end | 19 | (Back-end) Reset Password | Dinh | 4 | - | - | - | - | - | - | 2 | 2 | 0
| 18 | (Back-end) Forgot Password | Dinh | 4 | 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: 2; 2026-09-18: 2; 2026-09-19: 0
| 22 | (Back-end) Profile | Quy | 4 | - | - | - | - | - | - | - | 2 | 2 | 0
| 20 | (Back-end) Registration | Phuc | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 21 | (Back-end) Login | Thuan | 4 | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 23 | (Back-end) GitHub Repository | Dinh | 6 | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 0
| 24 | (Back-end) Environment Setup | Phuc | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 25 | (Back-end) Authentication Middleware | Thuan | 4 | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
| 26 | (Back-end) Snapshot Management | Quy | 4 | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 0
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 31 | Design Test Case for Profile | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 27 | Design Test Case for Registration | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 29 | Design Test Case for Forgot Password | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 30 | Design Test Case for Reset Password | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 32 | Design Test Case for Homepage | Thuan | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 33 | Design Test Case for Landscape | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 34 | Design Test Case for GitHub Repository | Dinh | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 35 | Design Test Case for Project Management | Quy | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
| 36 | Design Test Case for Snapshot | Phuc | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 0
|  |  | TOTAL | 112 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | -
|  |  | REMAIN | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -
ACTUAL
Conponent | No. | Task Name | Resposible Member | Estimate (hours) | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28
Design UI | 1 | UI Home Page | Thuan | 4
| 2 | UI Registration | Phuc | 2
| 5 | UI Forgot Password | Quy | 4
| 4 | UI Landscape | Dinh | 2
| 6 | UI Profile User | Phuc | 2
| 3 | UI Login | Dinh | 4
| 9 | UI Snapshot | Phuc | 2
| 7 | UI GitHub Repository | Thuan | 4
| 8 | UI Project | Thuan | 2
Database | 10 | Design database | Quy, Thuan | 8
Front end | 11 | (Front-end) Homepage | Quy | 4
| 14 | (Front-end) Login | Phuc | 4
| 15 | (Front-end) Forgot Password | Dinh | 2
| 12 | (Front-end) Landscape | Quy | 2
| 16 | (Front-end) GitHub Repository | Phuc | 4
| 13 | (Front-end) Registration | Thuan | 2
| 17 | (Front-end) Project Management | Quy | 2
Back end | 19 | (Back-end) Reset Password | Dinh | 4
| 18 | (Back-end) Forgot Password | Dinh | 4
| 22 | (Back-end) Profile | Quy | 4
| 20 | (Back-end) Registration | Phuc | 4
| 21 | (Back-end) Login | Thuan | 4
| 23 | (Back-end) GitHub Repository | Dinh | 6
| 24 | (Back-end) Environment Setup | Phuc | 4
| 25 | (Back-end) Authentication Middleware | Thuan | 4
| 26 | (Back-end) Snapshot Management | Quy | 4
Testing and fix bug | 28 | Design Test Case for Login | Phuc | 2
| 31 | Design Test Case for Profile | Dinh | 2
| 27 | Design Test Case for Registration | Dinh | 2
| 29 | Design Test Case for Forgot Password | Thuan | 2
| 30 | Design Test Case for Reset Password | Phuc | 2
| 32 | Design Test Case for Homepage | Thuan | 2
| 33 | Design Test Case for Landscape | Quy | 2
| 34 | Design Test Case for GitHub Repository | Dinh | 2
| 35 | Design Test Case for Project Management | Quy | 2
| 36 | Design Test Case for Snapshot | Phuc | 2
|  |  | TOTAL | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
|  |  | REMAIN | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | -
On Time
Lately
Early
Unfinished